## Bespoke Engineer Jobs This Week
CUSTOMER_ID | JOB_ID | POST_CODE | JOB_TYPE | JOB_STATUS | FAULT | JOB_BOOKED | APPOINTMENT_TIME | SCHEDULE_START_TIME | SCHEDULE_END_TIME | ON_SITE_TIME | CANCELLED_BY | CANCELLED_TIME | ENGINEER_ID | ENGINEER | COMPANY_NAME | SCHEDULE_DATE | REGION
6942225753 | 7344959 | ML2 7TT | Elec Only Install | Completed | Fault | 2021-01-10 17:48 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 09:13 |  |  | 16939 | JAMES MCLEAN | Bespoke Metering | 2021-01-11 | Scotland
3460673945 | 6355205 | G20 8EA | Elec Only Install | Completed | Fault | 2021-01-11 10:49 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 12:03 |  |  | 16415 | JOHN COYLE | Bespoke Metering | 2021-01-11 | Scotland
8510722650 | 4681691 | ML11 0BH | Gas Only Install | Completed | Fault | 2021-01-11 15:11 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 19:04 |  |  | 16436 | RICHARD JOHNSON01 | Bespoke Metering | 2021-01-11 | Scotland
7753902724 | 7360336 | TS26 0JA | Dual Fuel Install | Completed | Fault | 2021-01-11 10:43 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 12:19 |  |  | 16089 | MICHAEL SEAMAN | Bespoke Metering | 2021-01-11 | North East
4510043436 | 4860990 | EH11 4RY | Elec Only Install | Completed |  | 2020-07-23 05:17 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 11:07 |  |  | 16393 | GAVIN BROWN | Bespoke Metering | 2021-01-11 | Scotland
5423701304 | 5358741 | TS19 8QS | Dual Fuel Install | Completed | Fault | 2021-01-11 15:09 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 17:42 |  |  | 15200 | MICHAEL JENNINGS | Bespoke Metering | 2021-01-11 | North East
3427183313 | 7360362 | NE63 9TD | Elec Only Install | Completed | Fault | 2021-01-11 11:38 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 12:27 |  |  | 15152 | RICH BRANNEN | Bespoke Metering | 2021-01-11 | North East
9100370892 | 7048580 | NE34 0BZ | Dual Fuel Install | Completed |  | 2020-12-22 09:00 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 10:59 |  |  | 16264 | ANDREW BULFORD | Bespoke Metering | 2021-01-11 | North East
7933425165 | 7360426 | NE8 3ST | Gas Only Install | Completed | Fault | 2021-01-11 12:37 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 13:54 |  |  | 16264 | ANDREW BULFORD | Bespoke Metering | 2021-01-11 | North East
5567876945 | 7156591 | DG2 0QD | Gas Only Install | Completed | Fault | 2021-01-11 14:57 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 18:08 |  |  | 16457 | WILLIAM FLETCHER01 | Bespoke Metering | 2021-01-11 | Scotland
6661562152 | 7080897 | G78 1RJ | Elec Only Install | Completed | Fault | 2021-01-11 16:01 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 17:17 |  |  | 16436 | RICHARD JOHNSON01 | Bespoke Metering | 2021-01-11 | Scotland
6810300311 | 5151795 | TD14 5DS | Elec Only Install | Completed | Fault | 2021-01-11 14:46 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 18:27 | Supplier | 2020-09-07 11:30 | 17241 | MARTIN GORDON | Bespoke Metering | 2021-01-11 | Scotland
1823451163 | 7329295 | G22 7QX | Gas Only Install | Completed |  | 2021-01-08 16:14 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 09:16 |  |  | 16415 | JOHN COYLE | Bespoke Metering | 2021-01-11 | Scotland
4927736434 | 6725159 | NE11 9SS | Dual Fuel Install | Completed | Fault | 2021-01-11 11:21 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 14:52 |  |  | 16605 | DALE BURRELL | Bespoke Metering | 2021-01-11 | North East
6577049498 | 5275432 | SR3 2RT | Elec Only Install | Completed | Fault | 2021-01-11 11:49 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 14:31 | Supplier | 2020-09-17 14:50 | 17202 | MICHAEL CHARLTON | Bespoke Metering | 2021-01-11 | North East
4370885422 | 4863318 | KA20 3HD | Elec Only Install | Completed |  | 2020-07-23 05:17 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 10:58 |  |  | 16504 | THOMAS LEISK | Bespoke Metering | 2021-01-11 | Scotland
1001595100 | 7281570 | G53 7AU | Gas Only Install | Completed | Fault | 2021-01-11 12:10 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 13:00 |  |  | 16415 | JOHN COYLE | Bespoke Metering | 2021-01-11 | Scotland
2682110963 | 7360449 | PA2 9AW | Gas Only Install | Completed | Fault | 2021-01-11 13:54 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 15:08 |  |  | 16527 | ALISTAIR CAVAN | Bespoke Metering | 2021-01-11 | Scotland
5056818624 | 7360346 | TS1 5NE | Gas Only Install | Completed | Fault | 2021-01-11 10:03 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 12:25 |  |  | 16928 | MICHAEL BALL01 | Bespoke Metering | 2021-01-11 | North East
4349099289 | 7375806 | NE61 5YG | Gas Only Install | Completed | Fault | 2021-01-11 13:39 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 16:31 |  |  | 14881 | SIMON SNOWDON01 | Bespoke Metering | 2021-01-11 | North East
2332946557 | 2960108 | TS19 0DL | Elec Only Install | Completed | Fault | 2021-01-11 15:51 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 19:14 |  |  | 15200 | MICHAEL JENNINGS | Bespoke Metering | 2021-01-11 | North East
2386294485 | 7080044 | ML2 8NS | Dual Fuel Install | Completed | Fault | 2021-01-11 10:33 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 12:34 |  |  | 16939 | JAMES MCLEAN | Bespoke Metering | 2021-01-11 | Scotland
5818624150 | 7375849 | SR8 3SU | Elec Only Install | Completed | Fault | 2021-01-11 16:05 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 17:18 |  |  | 17202 | MICHAEL CHARLTON | Bespoke Metering | 2021-01-11 | North East
3107759491 | 7188811 | NE65 0GW | Gas Only Install | Completed | Fault | 2021-01-11 15:46 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 17:40 |  |  | 14881 | SIMON SNOWDON01 | Bespoke Metering | 2021-01-11 | North East
6290839443 | 5722587 | G81 1ND | Check Comms | Aborted | Fault | 2021-01-11 16:22 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 19:48 |  |  | 16527 | ALISTAIR CAVAN | Bespoke Metering | 2021-01-11 | Scotland
1205812555 | 5275996 | DD8 2DG | Gas Only Install | Completed | Fault | 2021-01-11 09:51 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 11:40 | Supplier | 2020-09-14 12:04 | 16497 | SHAUN HENDERSON | Bespoke Metering | 2021-01-11 | Scotland
3898612383 | 7204092 | PA16 0YP | Dual Fuel Install | Completed | Fault | 2021-01-11 15:19 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 17:41 |  |  | 16527 | ALISTAIR CAVAN | Bespoke Metering | 2021-01-11 | Scotland
6310555695 | 7188091 | G20 7HU | Elec Only Install | Completed | Fault | 2021-01-11 09:32 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 10:52 |  |  | 16415 | JOHN COYLE | Bespoke Metering | 2021-01-11 | Scotland
6310555695 | 7360373 | G20 7HU | Check Comms | Completed | Fault | 2021-01-11 09:32 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 20:02 |  |  | 16454 | ANDREW BRYDON01 | Bespoke Metering | 2021-01-11 | Scotland
6310555695 | 7188091 | G20 7HU | Elec Only Install | Completed | Fault | 2021-01-11 18:26 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 10:52 |  |  | 16415 | JOHN COYLE | Bespoke Metering | 2021-01-11 | Scotland
6310555695 | 7360373 | G20 7HU | Check Comms | Completed | Fault | 2021-01-11 18:26 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 20:02 |  |  | 16454 | ANDREW BRYDON01 | Bespoke Metering | 2021-01-11 | Scotland
6888498277 | 7360376 | G75 0PJ | Elec Only Install | Completed | Fault | 2021-01-11 11:50 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 14:41 |  |  | 16436 | RICHARD JOHNSON01 | Bespoke Metering | 2021-01-11 | Scotland
9699155533 | 7281619 | NE24 5RZ | Check Comms | Completed |  | 2021-01-06 08:50 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 11:46 |  |  | 15152 | RICH BRANNEN | Bespoke Metering | 2021-01-11 | North East
7805780713 | 7375804 | KA8 9SE | Gas Only Install | Completed | Fault | 2021-01-11 09:37 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 14:38 |  |  | 16504 | THOMAS LEISK | Bespoke Metering | 2021-01-11 | Scotland
7805780713 | 4614212 | KA8 9SE | Gas Only Install | Completed | Fault | 2021-01-11 09:37 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 13:21 | Customer | 2020-07-29 16:01 | 16504 | THOMAS LEISK | Bespoke Metering | 2021-01-11 | Scotland
8744237866 | 2831426 | TS19 9AH | Gas Only Install | Completed |  | 2019-11-21 12:14 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 08:07 | Supplier | 2019-12-20 15:47 | 16089 | MICHAEL SEAMAN | Bespoke Metering | 2021-01-11 | North East
8744237866 | 6972286 | TS19 9AH | Gas Only Install | Aborted |  | 2020-12-17 09:28 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 |  |  |  | 16454 | ANDREW BRYDON01 | Bespoke Metering | 2021-01-11 | North East
8893116126 | 2938792 | FK10 2NA | Check Comms | Aborted | Fault | 2021-01-11 16:29 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 17:52 |  |  | 16604 | CHRIS STEIN | Bespoke Metering | 2021-01-11 | Scotland
2288422475 | 5151318 | TS19 8BD | Dual Fuel Install | Completed | Fault | 2021-01-11 08:38 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 10:04 |  |  | 16089 | MICHAEL SEAMAN | Bespoke Metering | 2021-01-11 | North East
4008389974 | 7375840 | NE28 9EY | Gas Only Install | Completed | Fault | 2021-01-11 15:22 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 19:09 |  |  | 14881 | SIMON SNOWDON01 | Bespoke Metering | 2021-01-11 | North East
4781547947 | 7360281 | KY6 1JB | Gas Only Install | Completed | Fault | 2021-01-11 08:37 | PM | 2021-01-11 12:00 | 2021-01-11 17:00 | 2021-01-11 14:30 |  |  | 16393 | GAVIN BROWN | Bespoke Metering | 2021-01-11 | Scotland
6848904904 | 7360353 | DH3 3DP | Gas Only Install | Completed | Fault | 2021-01-11 10:16 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 13:16 |  |  | 16605 | DALE BURRELL | Bespoke Metering | 2021-01-11 | North East
5128596302 | 7329303 | KA21 5AZ | Check Comms | Completed |  | 2021-01-08 16:34 | AM | 2021-01-11 08:00 | 2021-01-11 13:00 | 2021-01-11 10:11 |  |  | 16504 | THOMAS LEISK | Bespoke Metering | 2021-01-11 | Scotland
3698888947 | 7375885 | DD11 1LQ | Dual Fuel Install | Completed | Fault | 2021-01-11 11:26 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 09:56 |  |  | 16497 | SHAUN HENDERSON | Bespoke Metering | 2021-01-12 | Scotland
7728004801 | 7360385 | ML6 8EB | Dual Fuel Install | Completed | Fault | 2021-01-11 12:13 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 14:08 |  |  | 16939 | JAMES MCLEAN | Bespoke Metering | 2021-01-12 | Scotland
7785743690 | 7375944 | TS7 9NG | Gas Only Install | On Site | Fault | 2021-01-11 19:18 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 19:17 |  |  | 15200 | MICHAEL JENNINGS | Bespoke Metering | 2021-01-12 | North East
2194519854 | 7376331 | NE9 5QQ | Dual Fuel Install | Completed | Fault | 2021-01-12 14:13 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 18:22 |  |  | 14881 | SIMON SNOWDON01 | Bespoke Metering | 2021-01-12 | North East
9568060486 | 5765168 | FK10 2TT | Gas Only Install | Completed | Fault | 2021-01-12 14:46 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 16:13 |  |  | 17241 | MARTIN GORDON | Bespoke Metering | 2021-01-12 | Scotland
9803986997 | 4876735 | NE6 2TH | Elec Only Install | Completed | Fault | 2021-01-12 12:21 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 15:37 |  |  | 14881 | SIMON SNOWDON01 | Bespoke Metering | 2021-01-12 | North East
3168284423 | 7376275 | SR8 4BN | Elec Only Install | Completed | Fault | 2021-01-12 08:55 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 14:26 |  |  | 17202 | MICHAEL CHARLTON | Bespoke Metering | 2021-01-12 | North East
4680530565 | 6862885 | DH5 0ED | Check Comms | Aborted | Fault | 2021-01-12 19:02 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 17:52 |  |  | 17202 | MICHAEL CHARLTON | Bespoke Metering | 2021-01-12 | North East
4680530565 | 7391905 | DH5 0ED | Dual Fuel Install | Completed | Fault | 2021-01-12 19:02 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 19:58 |  |  | 17202 | MICHAEL CHARLTON | Bespoke Metering | 2021-01-12 | North East
5863164990 | 6340167 | EH3 6RA | Dual Fuel Install | Completed | Fault | 2021-01-12 12:26 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 13:52 |  |  | 16393 | GAVIN BROWN | Bespoke Metering | 2021-01-12 | Scotland
2269608652 | 7391861 | TS28 5BL | Gas Only Install | Completed | Fault | 2021-01-12 14:55 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 17:21 |  |  | 15200 | MICHAEL JENNINGS | Bespoke Metering | 2021-01-12 | North East
6235195373 | 7313863 | DL17 8DP | Dual Fuel Install | Completed | Fault | 2021-01-12 11:04 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 13:16 |  |  | 16928 | MICHAEL BALL01 | Bespoke Metering | 2021-01-12 | North East
9376944125 | 7329278 | TD1 2JS | Dual Fuel Install | Completed |  | 2021-01-08 15:28 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 10:59 |  |  | 16605 | DALE BURRELL | Bespoke Metering | 2021-01-12 | Scotland
3349917325 | 4935152 | SR5 2HH | Dual Fuel Install | Aborted |  | 2020-07-27 09:15 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 10:03 |  |  | 14877 | TIM BONIFACE01 | Bespoke Metering | 2021-01-12 | North East
4381207230 | 7375990 | DL14 8LL | Elec Only Install | Completed | Fault | 2021-01-12 08:55 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 11:28 |  |  | 16928 | MICHAEL BALL01 | Bespoke Metering | 2021-01-12 | North East
5098267642 | 7391901 | G66 8DL | Gas Only Install | Completed | Fault | 2021-01-12 16:29 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 19:19 |  |  | 16436 | RICHARD JOHNSON01 | Bespoke Metering | 2021-01-12 | Scotland
2000179530 | 2936516 | KY7 4PN | Elec Only Install | Completed | Fault | 2021-01-12 12:49 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 14:15 |  |  | 16392 | CRAIG PATERSON 01 | Bespoke Metering | 2021-01-12 | Scotland
1982933384 | 7298241 | DH4 7LZ | Elec Only Install | Completed |  | 2021-01-07 11:32 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 14:34 |  |  | 15152 | RICH BRANNEN | Bespoke Metering | 2021-01-12 | North East
1951587970 | 7391854 | AB16 5TU | Gas Only Install | Completed | Fault | 2021-01-12 14:32 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 15:59 |  |  | 16510 | MARTIN STEPHEN | Bespoke Metering | 2021-01-12 | Scotland
9090531308 | 7313667 | NE9 5QH | Check Comms | Completed |  | 2021-01-07 18:00 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 16:25 |  |  | 16454 | ANDREW BRYDON01 | Bespoke Metering | 2021-01-12 | North East
5921724206 | 7313914 | NE10 0ET | Gas Only Install | Completed |  | 2021-01-08 11:41 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 09:04 |  |  | 16264 | ANDREW BULFORD | Bespoke Metering | 2021-01-12 | North East
7264534003 | 7376405 | KY7 6XW | Dual Fuel Install | Completed | Fault | 2021-01-12 11:31 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 12:39 |  |  | 16392 | CRAIG PATERSON 01 | Bespoke Metering | 2021-01-12 | Scotland
3767311972 | 6847382 | G22 7LJ | Elec Only Install | Completed | Fault | 2021-01-12 10:09 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 11:24 |  |  | 16415 | JOHN COYLE | Bespoke Metering | 2021-01-12 | Scotland
7672074961 | 7391833 | NE34 8RU | Gas Only Install | Completed | Fault | 2021-01-12 14:38 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 16:07 |  |  | 17202 | MICHAEL CHARLTON | Bespoke Metering | 2021-01-12 | North East
4866834233 | 7376379 | KA13 6HP | Gas Only Install | Completed | Fault | 2021-01-12 10:08 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 11:28 |  |  | 16504 | THOMAS LEISK | Bespoke Metering | 2021-01-12 | Scotland
8893116126 | 7375905 | FK10 2NA | Check Comms | Aborted | Fault | 2021-01-12 12:24 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 15:02 |  |  | 17241 | MARTIN GORDON | Bespoke Metering | 2021-01-12 | Scotland
2002024961 | 4862486 | EH8 9QY | Gas Only Install | Completed | Fault | 2021-01-12 15:18 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 16:49 |  |  | 16604 | CHRIS STEIN | Bespoke Metering | 2021-01-12 | Scotland
8037166611 | 4866848 | TS3 9EU | Gas Only Install | Completed | Fault | 2021-01-12 10:48 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 12:49 |  |  | 16089 | MICHAEL SEAMAN | Bespoke Metering | 2021-01-12 | North East
7084992605 | 7376408 | G31 1RQ | Elec Only Install | Completed | Fault | 2021-01-12 11:41 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 13:41 |  |  | 16415 | JOHN COYLE | Bespoke Metering | 2021-01-12 | Scotland
3264363242 | 7329413 | DH9 7SW | Gas Only Install | Completed | Fault | 2021-01-12 09:37 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 11:44 |  |  | 15152 | RICH BRANNEN | Bespoke Metering | 2021-01-12 | North East
8246792107 | 2364074 | NE34 7TF | Check Comms | Completed |  | 2018-12-21 13:47 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 11:08 | Customer | 2018-12-21 13:58 | 14885 | LIAM FLAHERTY01 | Bespoke Metering | 2021-01-12 | North East
3632536289 | 7376390 | G45 9RX | Elec Only Install | Completed | Fault | 2021-01-12 10:38 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 12:57 |  |  | 16415 | JOHN COYLE | Bespoke Metering | 2021-01-12 | Scotland
3992564630 | 6443443 | G33 3NN | Elec Only Install | Completed | Fault | 2021-01-12 16:36 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 17:41 |  |  | 16436 | RICHARD JOHNSON01 | Bespoke Metering | 2021-01-12 | Scotland
1508168303 | 7375987 | KA3 7QH | Check Comms | Aborted | Fault | 2021-01-12 08:44 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 14:03 |  |  | 16504 | THOMAS LEISK | Bespoke Metering | 2021-01-12 | Scotland
4380174832 | 7391900 | DL17 0DA | Elec Only Install | Completed | Fault | 2021-01-12 17:49 | PM | 2021-01-12 12:00 | 2021-01-12 17:00 | 2021-01-12 18:29 |  |  | 17202 | MICHAEL CHARLTON | Bespoke Metering | 2021-01-12 | North East
1480737765 | 7376377 | DD3 6LG | Elec Only Install | Completed | Fault | 2021-01-12 09:55 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 12:10 |  |  | 16497 | SHAUN HENDERSON | Bespoke Metering | 2021-01-12 | Scotland
8500558284 | 7313618 | SR8 3RB | Elec Only Install | Completed |  | 2021-01-07 15:55 | AM | 2021-01-12 08:00 | 2021-01-12 13:00 | 2021-01-12 08:51 |  |  | 16089 | MICHAEL SEAMAN | Bespoke Metering | 2021-01-12 | North East